## AT_b
Test Writer: Wes McEvoy
Test Case Name: |  | Acceptance Test: Beamforming |  |  |  |  | Test ID #: | 331
Description: |  | MRDs under test: 2, 4, 5, 7, 8, & 9 What is being tested: Integration of Lazy Harold electronics, Lazy Harold mechanical parts, and Beam Forming George FPGA configuration. How: We will be choosing a steering angle digitally using Beam Forming George's UI and then rotating our HackRF transmitter 180 degrees relative to the phased array (patch antennas) to produce antenna radiation patterns. We will produce a radiation pattern for steering angles of 0 and 30 degrees. What is measured: The received max powers of chunks of ADC samples from each step will be used to generate the normalized radiation pattern. The test will be a success if the peak of the main lobe (max power) is detected within +/- 1 degree of the inputted steering angle and the adjacent side lobes have peaks at least 10dB down from the peak of the steering angle lobe. What is expected: We are expecting our peak power to be around 1dBm and the side lobes to be at ~ -10 dBm. |  |  |  |  | Type: | Single
Tester Information
Name of Tester: |  | Katie Christiansen, Luke Hanley, Taylor Stevenson, Gabe Vitti, Erika Antunez, Wes McEvoy |  |  |  |  | Date: | 2024-04-11
Hardware Ver: |  | Hardware V3 |  |  |  |  | Time: | 8:30
Setup: |  | Setup: A portapack mounted on LH transmitting a 1.24GHz sine at ? dBm wave through a custom AFE PCB (Henrietta board) and a custom patch antenna. Array of custom patch antennas will be placed 1 foot away with each one connected to a Henrietta board and BFG via an ADC. LH will be be powered by a laptop and connected by an IO wire and GND wire to BFG. The stepper motor will be powered by a bench supply at 5V with current clamped at 2A. The Henriettas will be powered by a bench supply at 8V with current clamped at .5A. BFG will be powered using its supplied power cord connected to a standard wall outlet. Inputs: UI via JupyterWidgets for steering angle and flipping switch on RFSoC to start test sequence. 1.24GHz sine wave at ? dBm via HackRF. Outputs: Radiation pattern with side lobes 10 dB down from the peak power of the main lobe. Peak power of the main lobe should be seen within +/- 1 degree of the inputted steering angle. Special Conditions: LH will start at -90 degrees off of broadside. Software Elements: This test includes software to calculate power values and generate and display the radiation pattern in the form of a polar graph. We will also be using our custom FPGA configuration and scripts.
Test | Input parameter/Action | Expected Output | Pass | Fail | N/A | Actual Output
1 | ? dBm via HackRF. | Side lobes minimum of 10dBm down from main lobe.
2 | Steering angle via JupyterLabs | Peak power of main lobe within +/- 1 degree of inputted steering angle.
3
4
5
Overall Test Result:

## AT_a
Test Writer: Wes McEvoy
Test Case Name: |  | Acceptance Test: Kind of Beamforming |  |  |  |  | Test ID #: | 331
Description: |  | MRDs under test: 2, 4, 5, 8, & 9 What is being tested: Integration of Lazy Harold electronics, Lazy Harold mechanical parts, and custom phased array. How: We will sum signals analog using a splitter while rotating our HackRF transmitter 180 degrees relative to the phased array (patch antennas) to produce an antenna radiation pattern. What is measured: The received max powers of chunks of ADC samples from each step will be used to generate the normalized radiation pattern. The test will be a success if the peak of the main lobe (max power) is detected within +/- 5 degree of zero degrees and the adjacent side lobes have peaks at least 8dB down from the peak of the main angle lobe. Side lobes should also have peak power occurring within +/- 5 degrees of -45 and degrees. Two nulls or minima should be seen within +/- 5 degrees of -30 and 30 degrees. What is expected: We are expecting our peak power to be ~-3dBm. |  |  |  |  | Type: | Single
Tester Information
Name of Tester: |  | Katie Christiansen, Luke Hanley, Taylor Stevenson, Gabe Vitti, Erika Antunez, Wes McEvoy |  |  |  |  | Date: | 2024-04-11
Hardware Ver: |  | Hardware V3 |  |  |  |  | Time: | 10:00
Setup: |  | Setup: A portapack mounted on LH transmitting a 1.24GHz sine at 7.443125455 dBm wave through a custom AFE PCB (Henrietta board) and a custom patch antenna. Array of custom patch antennas will be placed 33.5 inches away with each one connected to a Henrietta board and BFG via an ADC. LH will be be powered by a laptop and connected by an IO wire and GND wire to BFG. The stepper motor will be powered by a bench supply at 8V with current clamped at 2A. The Henriettas will be powered by a bench supply at 8V with current clamped at .5A. BFG will be powered using its supplied power cord connected to a standard wall outlet. Inputs: UI via JupyterWidgets for steering angle and flipping switch on RFSoC to start test sequence. 1.24GHz sine wave at 7.443125455 dBm via HackRF. Outputs: Radiation pattern with side lobes 8 dB down from the peak power of the main lobe. Peak power of the main lobe should be seen within +/- 5 degree of 0 degrees. Special Conditions: LH will start at 90 degrees off of broadside. Software Elements: This test includes software to calculate power values and generate and display the radiation pattern in the form of a polar graph.
Test | Input parameter/Action | Expected Output | Pass | Fail | N/A | Actual Output
1 | 7.443125455 dBm via HackRF. | Peak power of main lobe within +/- 5 degree of 0 degrees.
2 | "" | Side lobes minimum of 8dBm down from main lobe.
3 | "" | Peak power of side lobes within +/- 5 degrees of -45 and 45 degrees.
4 | "" | Local minima occuring within +/- 5 degrees of -30 and 30 degrees.
5
Overall Test Result: